## 1_Agile_Template_Product_Backlo
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US-01 | As a student, I want to create an account and authenticate with JWT security, so that my career data and progress remain private and secure. | Must Have | None | Lokeswar | Done
Sprint 1 | Sprint 1 | US-02 | As a student, I want to set up my student profile with degree, university, graduation year, and skills, so that the AI understands my background. | Must Have | US-01 | Lokeswar | Done
Sprint 1 | Sprint 1 | US-03 | As a student, I want to upload my PDF/DOCX resume for automated Gemini AI parsing and skill extraction, so that I don't have to manually type my skills. | Must Have | US-02 | Lokeswar | Done
Sprint 1 | Sprint 1 | US-04 | As a candidate, I want to receive a SWOT analysis of my resume, so that I understand my strengths and skill gaps early on. | Should Have | US-03 | Lokeswar | Done
Sprint 2 | Sprint 2 | US-05 | As a student, I want to browse a verified catalog of 180+ tech internships, so that I can discover relevant opportunities. | Must Have | None | Lokeswar | Done
Sprint 2 | Sprint 2 | US-06 | As a system, I want to chunk internship postings into semantic units and generate dense vector embeddings (720 chunks), so that semantic retrieval is fast and accurate. | Must Have | US-05 | Lokeswar | Done
Sprint 2 | Sprint 2 | US-07 | As a student, I want a Job-Resume Matching Agent to calculate a multi-factor compatibility score with transparent reasoning, so that I understand my fit. | Must Have | US-03, US-06 | Lokeswar | Done
Sprint 2 | Sprint 2 | US-08 | As an evaluator, I want to benchmark matching accuracy across diverse student profiles, so that the matching engine achieves >85% MRR and >80% Top-1 accuracy. | Should Have | US-07 | Lokeswar | Done
Sprint 3 | Sprint 3 | US-09 | As a student, I want a 5-category Skill Gap Analysis Agent with personalized roadmaps, so that I know exactly what project to build to close my gaps. | Must Have | US-07 | Lokeswar | Done
Sprint 3 | Sprint 3 | US-10 | As an applicant, I want to generate ATS-optimized STAR bullet points and targeted cover letters with strict anti-hallucination guardrails, so that my applications stand out. | Must Have | US-03, US-07 | Lokeswar | Done
Sprint 3 | Sprint 3 | US-11 | As a candidate, I want an AI Mock Interview Coach with speech-to-text and 3D scoring (Technical, Communication, Relevance), so that I can practice interview questions. | Must Have | US-07, US-09 | Lokeswar | Done
Sprint 3 | Sprint 3 | US-12 | As a student, I want a Conversational Career Assistant orchestrator that retains multi-turn context and compares opportunities, so that I receive strategic guidance. | Should Have | US-09, US-10, US-11 | Lokeswar | Done
Sprint 4 | Sprint 4 | US-13 | As a student, I want a 10-Stage Application Lifecycle Tracker (Saved, Applied, Under Review, Shortlisted, Interview Scheduled, Interview Completed, Offer Received, Rejected, Withdrawn), so that I can manage my active pipeline. | Must Have | US-01, US-05 | Lokeswar | Done
Sprint 4 | Sprint 4 | US-14 | As a candidate, I want an Urgency Alert Engine and Kanban Drag-and-Drop + Table view, so that I never miss an application deadline. | Must Have | US-13 | Lokeswar | Done
Sprint 4 | Sprint 4 | US-15 | As a system evaluator, I want sub-300ms execution latency for API responses with deterministic fallback, so that the user experience is smooth and performant. | Must Have | US-07, US-10 | Lokeswar | Done
Sprint 4 | Sprint 4 | US-16 | As an evaluator, I want end-to-end system testing across all 4 milestones (105 test assertions), so that compliance and quality are verified. | Must Have | US-01 to US-15 | Lokeswar | Done