## 1_Agile_Template_Retrospection
Sprint | What Went Well? | What Could Be Improved? | Action Items / Decisions
Sprint 1 (M1) | Clean decoupled architecture; resilient fallback engine prevents Gemini API quota bottlenecks. | File parsing for complex multi-column PDFs needed better normalization. | Added regex-based entity cleaning before LLM prompting.
Sprint 2 (M2) | RAG vector search achieved 100% Top-1 accuracy and 1.000 MRR on benchmark tests. | Dense vector serialization in SQLite required optimized JSON parsing. | Cached 720 embedding chunks in memory on backend startup.
Sprint 3 (M3) | All 4 multi-agent features delivered with 100% automated test pass rate (31/31 assertions). | UI navigation needed intuitive collapse/expand controls on the left. | Implemented collapsible Left Sidebar with aligned bottom user widget and 3D background.
Sprint 4 (M4) | Delivered 10-Stage Application Kanban/Table Tracker, Urgency Reminders, Sub-300ms Performance Benchmarks, and 100% test pass rate across 105 total assertions. | Table filtering on application list required fine-tuning date calculations for overdue badges. | Refactored application utility functions for instant date diff calculations and seamless drag-and-drop state persistence.